## 2024 Jan Update
Important Notice This report includes anticipated dates, methods of delivery and estimated contract values that are based on the best available information at the time the report was last updated. The Washington State Department of Transportation (WSDOT) will update this report semi-annually and endeavors to ensure that the information contained herein is as accurate as possible, but cannot make any guarantees as to ultimate outcomes. Regardless of confidence rating, WSDOT is not responsible or liable to any parties if elements of this report are used to influence or inform the business decisions of those parties. * Information about delivery method may be useful to firms interested in (a) preparing for alternative project delivery scenarios or (b) identifying projects where work on preliminary design may result in the inability to work on subsequent design elements. ** These confidence ratings are qualitative judgements about whether the information presented will match the ultimate project scenario. See above notice.
Project | Description | Advertisement | Delivery Method* | A & E Category | Contract Execution Date | Estimated End Date | Region | Potential Value | Confidence Rating** | Project Contact Information
I-5/E Fork Lewis River Bridge NB - Replace Bridge | Provide engineering and related technical services as part of the Design Build Team to deliver the project. | 2024-02-26 | Design Build | Transportation Design Engineering | 2025-03-01 | 2029-03-31 | SW | $80-90 million | HIgh | Susan Fell. swrcceo@wsdot.wa.gov
I5/Guide Meridian Interchange Vicinity-Fish Passage | Provide engineering and related technical services as part of the Design Build Team to deliver the project. | 2024-04-08 | DB | Transportation Design Engineering | 2025-05-05 | Feb. 2027 | NWR | $50 million | Medium | Shane Spahr (360) 757-5990 SpahrS@WSDOT.WA.GOV
I-5/Secret Creek - Fish Passage | Provide engineering and related technical services as part of the Design Build Team to deliver the project. | 2023-08-28 | DB | Transportation Design Engineering | 2024-05-15 | Dec. 2026 | NWR | $50 million | High | Shane Spahr (360) 757-5990 SpahrS@WSDOT.WA.GOV
Geotechnical Engineering & Project Delivery 2023 - 2027 (FE-2) | The State Geotechnical Office requires the services of a Geotechnical Engineering firm to provide specialized geotechnical engineering expertise, report development, project delivery, construction support and related activities on large complex transportation projects statewide. | Feb - Mar 2024 | All Delivery Methods DBB, DB, PDB, EMERG. | Geotechnical Engineering Transportation Design Engineering Transportation Construction Support | TBD | 2027-12-31 | HQ | $10 Million | High | Andrew Fiske, (360)709-5456, fiskea@wsdot.wa.gov
Geotechnical Engineering & Project Delivery 2023 - 2027 (FE-3) | The State Geotechnical Office requires the services of a Geotechnical Engineering firm to provide specialized geotechnical engineering expertise, report development, project delivery, construction support and related activities on large complex transportation projects statewide. | Feb - Mar 2024 | All Delivery Methods DBB, DB, PDB, EMERG. | Geotechnical Engineering Transportation Design Engineering Transportation Construction Support | TBD | 2027-12-31 | HQ | $4 Million | High | Andrew Fiske, (360)709-5456, fiskea@wsdot.wa.gov
SR 518, Tukwila International Boulevard Station Bus Rapid Transit | This Sound Transit funded project consists of a new Bus Rapid Transit station. The station would serve eastbound and westbound BRT vehicles located at-grade within the STATE SR 518 right-of-way. The station will be east of the Tukwila International Boulevard (SR 99) interchange adjacent to the existing Tukwila International Boulevard Link light rail station. | 1/18/24 - 12/20/24 | Design Build | Project | 2025-01-30 | 2027-06-20 | NW | $100-200 Million | Medium | Andrew Ziegler, (425)450-2570, zieglea@wsdot.wa.gov
WSDOT
Projected Design Opportunities for Consultants